PROJECT PLANNING LOGIC

Medical Diagnosis Center (MDC) — ServiceNow Project

| Planning date | 14 October 2026 |
| --- | --- |
| Team ID | ServiceNow - 92 |
| Sprint duration | Six calendar days per sprint |

# 1. Agile Planning Terms

| Term | Meaning for MDC |
| --- | --- |
| Sprint | A fixed period in which the team works to complete a planned set of tasks. This plan uses four six-day sprints. |
| Epic | A large area of project work divided into smaller, deliverable user stories. |
| User Story | A small requirement written from the user’s perspective, describing what they need to do and why. |
| Story Point | A relative estimate of effort and complexity. Story points are not hours or days. |

# 2. Story Point Scale

| Story Points | Effort Level |
| --- | --- |
| 1 | Very easy task |
| 2 | Normal task |
| 3 | Moderate task |
| 5 | Difficult task |

# 3. Sprint-wise Epic and Story Plan

## Sprint 1 — Data Foundation and Access

Planned period: 22 to 27 Sep 2026 | Estimated total: 19 story points

| Epic | Story ID | User Story / Task | Points |
| --- | --- | --- | --- |
| E1 — Core Data Tables | USN-01 | Create Patient table and required patient fields | 3 |
| E1 — Core Data Tables | USN-02 | Create Diagnostic Test table with test name, category, description, price, duration and preparation instructions | 3 |
| E1 — Core Data Tables | USN-03 | Create Appointment table with patient/test references and status choices | 3 |
| E1 — Core Data Tables | USN-04 | Create Medical Report table and patient/appointment references | 3 |
| E2 — Catalog and Roles | USN-05 | Add and verify active diagnostic-test records | 2 |
| E2 — Catalog and Roles | USN-06 | Configure admin, patient, receptionist and lab-technician roles | 5 |
| Sprint total |  |  | 19 |

## Sprint 2 — Service Portal and Booking

Planned period: 28 Sep –3 Oct 2026 | Estimated total: 16 story points

| Epic | Story ID | User Story / Task | Points |
| --- | --- | --- | --- |
| E3 — Portal and Booking | USN-07 | Set up portal home page and navigation | 2 |
| E3 — Portal and Booking | USN-08 | Display active diagnostic tests and their details in the catalog | 3 |
| E3 — Portal and Booking | USN-09 | Build Book a Test form with required-field validation | 5 |
| E3 — Portal and Booking | USN-10 | Save appointments linked to the selected patient and test | 3 |
| E3 — Portal and Booking | USN-11 | Build My Appointments view with appointment details and status | 3 |
| Sprint total |  |  | 16 |

## Sprint 3 — Appointment Workflow and Reports

Planned period: 3 Oct – 8 Oct 2026 | Estimated total: 17 story points

| Epic | Story ID | User Story / Task | Points |
| --- | --- | --- | --- |
| E4 — Appointment Workflow | USN-12 | Allow authorized staff to update appointment status | 3 |
| E5 — Report Generation | USN-13 | Create a linked report when an appointment changes to Completed and prevent duplicates | 5 |
| E5 — Report Generation | USN-14 | Populate report number, date, patient, appointment and demonstration findings | 3 |
| E5 — Report Generation | USN-15 | Display available reports and findings in Medical Reports | 3 |
| E6 — Notifications | USN-16 | Configure booking/report email notifications when outbound email is enabled | 3 |
| Sprint total |  |  | 17 |

## Sprint 4 — Report Access, Testing and Delivery

Planned period:  8 Oct – 13 Oct 2026 | Estimated total: 18 story points

| Epic | Story ID | User Story / Task | Points |
| --- | --- | --- | --- |
| E7 — Report Access | USN-17 | Provide and verify the print/save report flow and Download Report action | 3 |
| E8 — Security and QA | USN-18 | Test role permissions and patient-specific record access | 5 |
| E8 — Security and QA | USN-19 | Run end-to-end tests and resolve workflow or data-linking issues | 5 |
| E8 — Security and QA | USN-20 | Polish form validation, labels, reference displays and portal messages | 3 |
| E9 — Project Delivery | USN-21 | Prepare project documentation, screenshots and demonstration steps | 2 |
| Sprint total |  |  | 18 |

# 4. Total Story Points and Velocity

| Sprint | Estimated Story Points | Planned Duration |
| --- | --- | --- |
| Sprint 1 | 19 | 6 days |
| Sprint 2 | 16 | 6 days |
| Sprint 3 | 17 | 6 days |
| Sprint 4 | 18 | 6 days |
| Total / planned average | 70 points / 17.5 per sprint | 4 sprints |

Planned average workload = 70 estimated story points ÷ 4 planned sprints = 17.5 story points per sprint. This is an estimate, not measured team velocity. Actual velocity is calculated by dividing the number of story points actually completed by the number of completed sprints.